MEMORANDUM FOR THE RECORD

Date:	2/15/2005

To:	Mark Mitsuyasu

Cc:	Francis G. Oishi; Michael Fujimoto

From:	Earl Miyamoto

RE:	FISHERIES DISASTER RELIEF EXECUTIVE STEERING COMMITTEE FORMULATION MEETING OF 14 FEBRUARY 2005

- Participants – Earl Miyamoto; Mark Mitsuyasu

- We discussed the contract being worked up by JIMAR and decided we needed to see the completed proposal to determine what would be provided regarding admin support; outreach and area content before we could formulate a timeline/plan for working with fishermen.

- We tentatively looked at the week of 7-11 March 2005 for the first ESC meeting.   This was based on the 1 March 2005 date agreed upon by Mr. Tom Schroeder to present a proposal from JIMAR at the meting of 27 January 2005.  This would allow a week to conduct a preliminary review of the contract prior to the meeting.  This would also avoid delaying action on the contract with the Council Meeting scheduled for 14-17 March 2005 and the “Managing Our Nations Fisheries Conference II” the following week   precluding the ESC members meeting during that timeframe.

- I proposed the agenda for the first meeting to cover the following areas:

  - Orientation/Information for the members

  - Reviewing the proposed contract

  - Forming the Technical Working Group (TWG)

  - Determining the scope/parameters for the TWG

- We agreed the TWG membership should be comprised of members with specific skill sets rather than be based on agency representation with the exception of the State representative who would be designated by DLNR and chair the group.  The commodity areas are:

  - Fishery Operations

  - Research

  - Data

  - Socio-economic

  - Science Multi-discipline

  - Outreach

  - Industry

- We formulated a list of two to three candidates for each area with the exception of the Science Multi-discipline area for ESC consideration.

- We agreed you would look at the scope of work for existing working groups at the Council and provide me with your ideas for the TWG.  I would do the same and we would work this issue via email to come up with a template to propose to the ESC.

- We discussed utilizing Mr. Tom Brower to do the initial research on other Fisheries Disaster Relief programs in the country vice hiring a consultant as discussed during the 27 January 2005 meeting.    You provided me with two names as points of contact for Mr. Brower to begin his research.

EMM